🔴 URGENT — Do these first (this week):

- Send Kyle's email — everything depends on confirming the SIG co-organization. The longer you wait the tighter the timeline

- Talk to your school (IUSJC) — confirm the venue, the date (May 18), and what equipment they'll provide. Nothing is real until the venue is locked

- Design your Amplify logo — you need this before any materials are made

🟠 SHORT TERM — Once venue and SIG are confirmed:

- Launch your volunteer call — open announcement on campus + personal recruitment for leads. You said you already have people in mind for leads so approach them first privately

- Send the IYC13 logo permission follow-up if no response yet

- Open your Instagram account — Amplify is your launch moment, the account should exist before outreach starts

🟡 PARALLEL — Can happen simultaneously with the above:

- Design event materials — banner, pledge form, certificate template, badges. Your Communication lead can handle this once recruited

- Draft the school outreach letter — we already have the template, just finalize it with confirmed date and venue details

- Identify your panel speakers — you need 2. Start reaching out early, speakers need notice

🟢 LATER — Once outreach begins:

- Ground outreach to schools and institutions — visits, letter drops, pledge form distribution

- Sponsor outreach — ISOC SIG budget conversation with Kyle + approach enterprises

- Volunteer orientation session — one week before May 18

- Set up Zoom free trial — activate one week before the event

# OVERALL STRATEGY

Position Amplify as:

A national youth peace movement powered by digital engagement

# 1. BEFORE THE EVENT (3–4 WEEKS)

## Goal:

Build hype + collect early pledges + recruit participants

## WEEK 1 (Launch Phase)

### Actions:

- Announce selection (IYC13 delegate)

- Introduce Amplify

- Launch Peace Pledge (soft)

### Content ideas:

- “I got selected…” (storytelling post)

- “What does peace mean to you?”

- Teaser: “Something big is coming for Cameroonian youth”

## WEEK 2 (Engagement Phase)

### Actions:

- Start school outreach

- Recruit digital ambassadors

### Content:

- Short videos: youth answering “What is peace?”

- Carousel: “Why youth matter in peacebuilding”

- Introduce speakers (if any)

## WEEK 3 (Conversion Phase)

### Actions:

- Push registrations

- Push pledge signing

### Content:

- Countdown posts (5 days, 3 days…)

- Testimonials

- “Join 500+ youth already committed”

## WEEK 4 (Final Push)

### Actions:

- Confirm attendance

- Final reminders

### Content:

- “Tomorrow is the day”

- Behind-the-scenes prep

- Speaker highlights

# 2. DURING THE EVENT (VERY IMPORTANT)

## Goal:

MAXIMUM visibility + real-time engagement

### Actions:

- Livestream key moments

- Post every 30–60 minutes

- Capture testimonials

### Content:

- Live quotes from speakers

- Photos of participants signing pledge

- Short videos (energy, crowd, activities)

- “We just reached 1,000 pledges 🔥”

### MUST DO:

👉 Assign a Media Team (VERY IMPORTANT)

- 1 for Instagram

- 1 for video

- 1 for photos

# 3. AFTER THE EVENT (MOST PEOPLE FAIL HERE)

## Goal:

Turn event → long-term impact

### Actions:

- Share results

- Thank partners

- Publish impact

### Content:

- “2,000 youth committed to peace”

- Recap video

- Photo dump

- Testimonials

### STRONG MOVE:

👉 Publish:

“Official Amplify Peace Pledge List (Names & Schools)”

This gives:

- Credibility

- Visibility

- Legacy

# STAKEHOLDER STRATEGY

### Schools

- Compete: “Top school with most pledges”

- Feature them online

### ISOC

- Tag them in digital posts

- Highlight digital impact

### Sponsors

- Offer visibility:

  - Logos

  - Mentions

  - Posts

# BONUS: VIRAL IDEA

Create:

“I Pledge for Peace” challenge

Participants:

- Post photo/video

- Tag 3 friends

- Use hashtag